## Sheet1
| Project Name | Project Duration | Project Start Date | Project End Date
ITEC 3040 Assignment 1
Task ID | Task Description | Task Duration | Start Date | End Date
1 | First Group Meeting (Determine Project Roles and Objectives) | 1 | 2020-09-19 | 2020-09-19
2 | Data Cleaning | 1 | 2020-09-20 | 2020-09-20
3 | Second Group Meeting (Discuss Findings) | 1 | 2020-09-21 | 2020-09-21
4 | EDA Creation | 6 | 2020-09-22 | 2020-09-28
5 | Create Report for Second Checkpoint | 4 | 2020-09-28 | 2020-10-02
6 | Create Presentation for Second Checkpoint | 2 | 2020-10-02 | 2020-10-04
7 | Third Group Meeting (Discuss Model Creation Based of EDA findings) | 1 | 2020-11-12 | 2020-11-13
8 | Create Prediction Model | 10 | 2020-11-13 | 2020-11-23
9 | Fourth Group Meeting (Discuss Prediction Model) | 1 | 2020-11-23 | 2020-11-24
Formulas:
Project End Date = [Project Start Date]+[Project Duration]
Project Start Date = [Project End Date, row above]